## Slide 1: Graveyard Spit Restoration and Resilience Project
Presented by:
Henry Bell, Washington State Department of Ecology
Dave Michalsen, U.S. Army Corps of Engineers
Garret Jackson, Washington State Department of Transportation
Chelsey Martin, Washington State Department of Transportation

## Slide 2: This project will address…
Problem:
  High energy shoreline area
  Rapid shoreline erosion from Pacific Ocean tidal action
Issue:
  Compromised State Route (SR) 105 roadway
  Loss of wetland and critical areas
Regional Priority: High
  Only access that connects the Shoalwater Bay Reservation and Tokeland to the south & Grayland, Cranberry Farms to the north
North Cove
Willapa Bay
Pacific Ocean

## Slide 3: A long history of shoreline retreat

## Slide 4
Decades of projects
On-going Maintenance
WSDOT Background

## Slide 5
Strategy to Address the Problem
Dynamic
Revetments

## Slide 6: Using natural analog beach

## Slide 7: Update on Implementation - Design
- Ground Survey
- Drone
- LiDAR
- Bathometric Survey - Scenario Layouts - Preliminary Design

## Slide 9
Winter storm
Mild summer condition
WAVE HEIGHT
southwesterly
northwesterly
Army Corps Modeling -

## Slide 10
Max, Median, Min
Max, Median, Min
NEARSHORE WAVE HEIGHT
Depth limited waves

## Slide 11
CURRENTS
Peak ebb: 12/11/15 01:00 UTC
Max speeds > 2m/s (4 knots)
Notes: Dave - CURRENTS

## Slide 12: Update on Implementation – Project’s APE
Start of Tribal Coordination & initiation of Section 106
NEXT STEPS –
Rights of Entry
Delineations
  Marine Ordinary High Water Mark (OHWM)
  Wetland Delineation
  High Tide Line (HTL)
  Mean higher high water (MHHW)
Shoalwater Bay Tribe

## Slide 13: Update on Implementation
Environmental Documentation & Permitting
NEPA Environmental Assessment (EA)
SEPA Adoption of NEPA EA
Endangered Species Act (ESA) Consultation
  NOAA – National Marine Fisheries Service (NMFS)
  United States Fish and Wildlife Service (USFWS)
Section 106 & Tribal Coordination
Army Corps Individual Section 404 / Section 10
Ecology & EPA - Section 401 / CZM
Washington Department of Fish and Wildlife (WDFW) Hydraulic Project Approval (HPA)
Pacific County Shoreline & CAO
Coordination with State Parks, DNR & WECAN

## Slide 14: Anticipated Environmental Challenges
ESA Listed Species & Public Access Concerns
  Western Snowy Plover
  Streaked Horned Lark
    Formal ESA Consultation (~1yr for Biological Opinion)
    BiOp commitments may including:
      Work Timing Restrictions – nesting windows
      Temporary site closures & monitoring
Marine In-water Work Window (IWWW)
Critical Areas Mitigation Costs Unknown
  On-site restoration vs. Mitigation Bank Credits
NEPA & Permitting to be completed by Spring 2023
  Environmental is Critical Path to Construction*
Streaked Horned Lark
Western Snowy Plover

## Slide 15: Activities to Address the Problem
Continued Coordination:
Public Involvement & Subcommittees

## Slide 16: Anticipated Implementation Challenges & Next Steps
Processes delayed due to COVID19
Timeline of large scale construction project
  On-going erosion threatening SR105
  Looking into interim solutions
Required Real Estate
  Which agency to take the lead
Construction funding unknown
  Looking into Local, State & Federal funding
  Early cost estimates for Construction ~$24 million
  Monitoring and Adaptive Management

## Slide 17: Thank you!
Graveyard Spit Restoration and Resilience Project
More information and updates may be found on the WECAN webpage:
Projects – WECAN | Washington Coastal Hazards Resilience Network (wacoastalnetwork.com)